## TAISNIERES H_REC
Interconnection Point* : IR0060 TAISNIERES H REC | [9 empty] | 2021
Units of measurement : GWh/day
| FIRM capacity |  |  |  | INTERRUPTIBLE capacity |  |  |  | PERIOD (days) | NATURE OF PLANNED MAINTENANCE
Period of maintenance (dd/mm <-> dd/mm) | FIRM CAPACITY (GWh/day) | PLANNED INTERRUPTION (Gwh/day) | REMAINING CAPACITY (Gwh/day) | REMAINING CAPACITY (%) | INTERRUPTIBLE CAPACITY (Gwh/day) | PLANNED INTERRUPTION (Gwh/day) | REMAINING CAPACITY (Gwh/day) | REMAINING CAPACITY (%)
07/06 <-> 13/06 | 638 | 260 | 378 | 59 % | 20 | 20 | 0 | 0 % | 7 | Compressor Station shudown Voisines
14/06 <-> 30/06 | 638 | 332 | 306 | 48 % | 20 | 20 | 0 | 0 % | 17 | Pipe repair Morelmaison-Voisines
01/07 <-> 02/07 | 638 | 334 | 304 | 48 % | 20 | 20 | 0 | 0 % | 2 | Pipe repair Morelmaison-Voisines
26/07 <-> 30/07 | 638 | 308 | 330 | 52 % | 20 | 20 | 0 | 0 % | 5 | Compressor Station shudown Cuvilly
02/08 <-> 13/08 | 638 | 310 | 328 | 51 % | 20 | 20 | 0 | 0 % | 12 | Compressor Station shudown Cuvilly
14/08 <-> 15/08 | 638 | 278 | 360 | 56 % | 20 | 20 | 0 | 0 % | 2 | Compressor Station shudown Cuvilly
23/08 <-> 27/08 | 638 | 182 | 456 | 71 % | 20 | 20 | 0 | 0 % | 5 | Pipe repair Arc de Dierrey
06/09 <-> 08/09 | 638 | 388 | 250 | 39 % | 20 | 20 | 0 | 0 % | 3 | Maintenance valve border point (Troll pipeline)
09/09 <-> 10/09 | 638 | 356 | 282 | 44 % | 20 | 20 | 0 | 0 % | 2 | Pipe repair Nord 1 (Taisnieres-Cuvilly)
11/09 <-> 12/09 | 638 | 252 | 386 | 61 % | 20 | 20 | 0 | 0 % | 2 | Pipe repair Nord 1 (Taisnieres-Cuvilly)
13/09 <-> 17/09 | 638 | 374 | 264 | 41 % | 20 | 20 | 0 | 0 % | 5 | Pipe repair Nord 1 (Taisnieres-Cuvilly)
04/10 <-> 15/10 | 638 | 248 | 390 | 61 % | 20 | 20 | 0 | 0 % | 12 | Pipe repair Nord 1 and pipeline pigging inspection Lorraine 1
23/10 <-> 29/10 | 638 | 423 | 215 | 34 % | 20 | 20 | 0 | 0 % | 7 | Pipe repair Marche du Nord Est
* Please consult also the adjacent TSO's website

## DUNKERQUE_REC
Interconnection Point* : IR0006 DUNKERQUE REC | [9 empty] | 2021
Units of measurement : GWh/day
| FIRM capacity |  |  |  | INTERRUPTIBLE capacity |  |  |  | PERIOD (days) | NATURE OF PLANNED MAINTENANCE
Period of maintenance (dd/mm <-> dd/mm) | FIRM CAPACITY (GWh/day) | PLANNED INTERRUPTION (Gwh/day) | REMAINING CAPACITY (Gwh/day) | REMAINING CAPACITY (%) | INTERRUPTIBLE CAPACITY (Gwh/day) | PLANNED INTERRUPTION (Gwh/day) | REMAINING CAPACITY (Gwh/day) | REMAINING CAPACITY (%)
18/05 <-> 18/05 | 569 | 184 | 385 | 68 % | 36 | 36 | 0 | 0 % | 1 | Annual Pitgam Interconnection grid full ESD Tests
07/06 <-> 08/06 | 569 | 134 | 435 | 76 % | 36 | 36 | 0 | 0 % | 2 | Compressor station Pitgam shutdown maintenances
09/06 <-> 10/06 | 569 | 469 | 100 | 18 % | 36 | 36 | 0 | 0 % | 2 | Compressor station Pitgam shutdown maintenances and Loon shutdown
11/06 <-> 11/06 | 569 | 329 | 240 | 42 % | 36 | 36 | 0 | 0 % | 1 | Compressor station Pitgam shutdown maintenances
23/08 <-> 27/08 | 569 | 142 | 427 | 75 % | 36 | 36 | 0 | 0 % | 5 | Pipe repair Arc de Dierrey
* Please consult also the adjacent TSO's website

## OBERGAILBACH_REC
Interconnection Point* : IR0010 OBERGAILBACH REC | [9 empty] | 2021
Units of measurement : GWh/day
| FIRM capacity |  |  |  | INTERRUPTIBLE capacity |  |  |  | PERIOD (days) | NATURE OF PLANNED MAINTENANCE
Period of maintenance (dd/mm <-> dd/mm) | FIRM CAPACITY (GWh/day) | PLANNED INTERRUPTION (Gwh/day) | REMAINING CAPACITY (Gwh/day) | REMAINING CAPACITY (%) | INTERRUPTIBLE CAPACITY (Gwh/day) | PLANNED INTERRUPTION (Gwh/day) | REMAINING CAPACITY (Gwh/day) | REMAINING CAPACITY (%)
07/06 <-> 13/06 | 618 | 286 | 332 | 54 % | 30 | 30 | 0 | 0 % | 7 | Compressor Station shudown Voisines
14/06 <-> 30/06 | 618 | 349 | 269 | 44 % | 30 | 30 | 0 | 0 % | 17 | Pipe repair Morelmaison-Voisines
01/07 <-> 02/07 | 618 | 352 | 266 | 43 % | 30 | 30 | 0 | 0 % | 2 | Pipe repair Morelmaison-Voisines
26/07 <-> 30/07 | 618 | 328 | 290 | 47 % | 30 | 30 | 0 | 0 % | 5 | Compressor Station shudown Cuvilly
02/08 <-> 13/08 | 618 | 331 | 287 | 46 % | 30 | 30 | 0 | 0 % | 12 | Compressor Station shudown Cuvilly
14/08 <-> 15/08 | 618 | 303 | 315 | 51 % | 30 | 30 | 0 | 0 % | 2 | Compressor Station shudown Cuvilly
09/09 <-> 10/09 | 618 | 370 | 248 | 40 % | 30 | 30 | 0 | 0 % | 2 | Pipe repair Nord 1 (Taisnieres-Cuvilly)
11/09 <-> 12/09 | 618 | 279 | 339 | 55 % | 30 | 30 | 0 | 0 % | 2 | Pipe repair Nord 1 (Taisnieres-Cuvilly)
13/09 <-> 17/09 | 618 | 387 | 231 | 37 % | 30 | 30 | 0 | 0 % | 5 | Pipe repair Nord 1 (Taisnieres-Cuvilly)
* Please consult also the adjacent TSO's website

## TAISNIERES B_REC
Interconnection Point* : IR0015 TAISNIERES B REC | [9 empty] | 2021
Units of measurement : GWh/day
| FIRM capacity |  |  |  | INTERRUPTIBLE capacity |  |  |  | PERIOD (days) | NATURE OF PLANNED MAINTENANCE
Period of maintenance (dd/mm <-> dd/mm) | FIRM CAPACITY (GWh/day) | PLANNED INTERRUPTION (Gwh/day) | REMAINING CAPACITY (Gwh/day) | REMAINING CAPACITY (%) | INTERRUPTIBLE CAPACITY (Gwh/day) | PLANNED INTERRUPTION (Gwh/day) | REMAINING CAPACITY (Gwh/day) | REMAINING CAPACITY (%)
13/07 <-> 13/07 | 229 | 229 | 0 | 0 % | 50 | 50 | 0 | 0 % | 1 | Maintenance valve border point
* Please consult also the adjacent TSO's website

## OLTINGUE_DEL
Interconnection Point* : IR0011 OLTINGUE DEL | [9 empty] | 2021
Units of measurement : GWh/day
| FIRM capacity |  |  |  | INTERRUPTIBLE capacity |  |  |  | PERIOD (days) | NATURE OF PLANNED MAINTENANCE
Period of maintenance (dd/mm <-> dd/mm) | FIRM CAPACITY (GWh/day) | PLANNED INTERRUPTION (Gwh/day) | REMAINING CAPACITY (Gwh/day) | REMAINING CAPACITY (%) | INTERRUPTIBLE CAPACITY (Gwh/day) | PLANNED INTERRUPTION (Gwh/day) | REMAINING CAPACITY (Gwh/day) | REMAINING CAPACITY (%)
01/10 <-> 22/10 | 259 | 259 | 0 | 0 % | 0 | 0 | 0 | 0 % | 22 | Pipe repair Morelmaison-Oltingue and Compressor station Morelmaison shutdown
23/10 <-> 29/10 | 259 | 119 | 140 | 54 % | 0 | 0 | 0 | 0 % | 7 | Compressor station Morelmaison partial shutdown
* Please consult also the adjacent TSO's website

## OLTINGUE_REC
Interconnection Point* : IR0011 OLTINGUE REC | [9 empty] | 2021
Units of measurement : GWh/day
| FIRM capacity |  |  |  | INTERRUPTIBLE capacity |  |  |  | PERIOD (days) | NATURE OF PLANNED MAINTENANCE
Period of maintenance (dd/mm <-> dd/mm) | FIRM CAPACITY (GWh/day) | PLANNED INTERRUPTION (Gwh/day) | REMAINING CAPACITY (Gwh/day) | REMAINING CAPACITY (%) | INTERRUPTIBLE CAPACITY (Gwh/day) | PLANNED INTERRUPTION (Gwh/day) | REMAINING CAPACITY (Gwh/day) | REMAINING CAPACITY (%)
09/03 <-> 09/03 | 100 | 100 | 0 | 0 % | 100 | 100 | 0 | 0 % | 1 | Reverse flow valve maintenance
14/06 <-> 02/07 | 100 | 100 | 0 | 0 % | 100 | 100 | 0 | 0 % | 19 | Pipe repair Morelmaison-Voisines
01/10 <-> 22/10 | 100 | 100 | 0 | 0 % | 100 | 100 | 0 | 0 % | 22 | Pipe repair Morelmaison-Oltingue
* Please consult also the adjacent TSO's website